## Delivery Plan
Staffordshire County Council Bus Service Improvement Delivery Plan 2025-26
Category of scheme/measure [select from drop down list] | Name of scheme/measure | Additional description of scheme/measure (including intended beneficial outcomes) | Target delivery date | Budget/estimated cost (£k) |  |  | (of which) 2025-26 Bus Grant (£k) |  |  | (of which) previous years' DfT BSIP funding (£k) |  |  | (of which) Other funding (£k) |  |  | Notes on other funding sources (identifying non-BSIP funding)
|  |  |  | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total
Bus service support/network development | Support of existing (as at 31/3/25) bus services | Maintaining the network that exists as of 31/3/25 | 1/4/25 ongoing | 0 | 5594 | 5594 | 0 | 1642 | 1642 | 0 | 3952 | 3952 |  |  | 0 | note - we are assuming you use the roll-forward before starting the 25-26 allocation. The roll-forward from 25-26 will be used in 26-27 to maintain services assuming 26-27 revenue funding is similar to 25-26
Bus service support/network development | New bus routes | 2 new routes 1 serving baswich, Brocton, Wildwood and the other (with details TBC) serving settlements in central Staffordshire without a current service | 2025-10-31 | 0 | 381 | 381 | 0 | 381 | 381 | 0 | 0 | 0 |  |  | 0
Bus service support/network development | Enhancement of bus routes | 4 routes enhanced operations | 2025-10-31 | 0 | 412 | 412 | 0 | 412 | 412 | 0 | 0 | 0 |  |  | 0
Bus service support/network development | Support of existing (as at 31/3/26) bus services beyond March 2026 | Maintaining the network that exists as of 31/3/26 at least until September 2026 | 2026-04-01 |  | 3254 | 3254 |  | 3254 | 3254
Bus stops/stations/interchanges | Improvements to Leek Bus Station | CCTV, new RTI system, cosmetic improvements | 2026-03-31 | 120 | 0 | 120 | 120 | 0 | 120 | 0 | 0 | 0 |  |  | 0
Bus stops/stations/interchanges | Improvements to Rugeley Bus Station | CCTV, new RTI system, cosmetic improvements | 2026-03-31 | 128 | 0 | 128 | 128 | 0 | 128 | 0 | 0 | 0 |  |  | 0
Bus stops/stations/interchanges | Improvements to Cannock Bus Station | CCTV, new RTI system, cosmetic improvements | 2026-03-31 | 200 | 0 | 200 | 200 | 0 | 200 | 0 | 0 | 0 |  |  | 0
Bus stops/stations/interchanges | Installation of real time displays | Installation of RTI to bus stops and totems to town centres to provide passenger information | 2027-03-31 | 3663 | 0 | 3663 | 3663 | 0 | 3663 | 0 | 0 | 0 |  |  | 0 | S106 if any becomes available will add to planned improvements
Bus stops/stations/interchanges | Bus stop improvements - accessibility | Improvements to bus stops - hardstanding, raised kerbs, dropped crossing access and shelters to improve accessibility to stops | 2027-03-31 | 750 | 125 | 875 | 750 | 125 | 875 | 0 | 0 | 0 |  |  | 0 | S106 if any becomes available will add to planned improvements. The £125k is the former Capacity fund, and is used to survey existing stops and identify requirements
Development of future proposals | Lichfield Bus Station replacement | Surveys to identify replacement options for Lichfield bus Station which District council are selling for redevelopment | 2027-03-31 | 400 | 0 | 400 | 400 | 0 | 400 | 0 | 0 | 0 |  |  | 0
LTA delivery/admin costs | additional team support, survey work, administration |  | 2026-03-31 | 0 | 80 | 80 | 0 | 80 | 80 | 0 | 0 | 0 |  |  | 0 | This will probably grow as further requirements to plan for 26/27 onwards are identified once longer term funding is known
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 5261 | 9846 | 15107 | 5261 | 5894 | 11155 | 0 | 3952 | 3952 | 0 | 0 | 0
Revenue
Note - the estimated costs and sources are figures for 25/26 financial year only
As previously supplied, the remainder of 25/26 Bus Grant will be used by September 2026 to continue to support the same services
Activities beyond that date will depend on 26/27 funding, options have previously been supplied with two "what if" scenarios at the extreme ends of funding
Capital
As previously advised if capacity permits, individual sites planned for 26-27 will be pulled forward. Figures reflect 25/26 spend
It is expected that the remainder of 25/26 capital spend along with 26/27 allocation (if any) will be spent in 26/27 as capacity constraints will be less with longer notice of allocation allowing planning in advance
All "Improvement" costs are estimated as schemes are only planned, detailed costs not yet available
Plans for any 26-27 grant will be developed once amounts are announced, with the aim of having detail of schemes 3 months after confirmation