## Programme
Programme Name: |  |  |  |  | Preventative Treatments (Footway)
Programme Reporting Period: |  |  |  |  | March 2025 - March 2026
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Area | Div | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
[6 empty] | Start Point | Finish Point
D2413 | W1 | North | 37601404 | Tiling Drive | Stone | B5026 Eccleshall Road | Beacon Rise | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601049 | Friars Avenue | Stone | Tiling Drive | Tiling Drive | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601179 | Austin Close | Stone | Friars Avenue | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601659 | Ernald Gardens | Stone | Friars Avenue | ends | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601696 | Clinton Gardens | Stone | Friars Avenue | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601323 | Cannons Close | Stone | Friars Avenue | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37602111 | Downing Gardens | Stone | Friars Avenue | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604266 | Brandon Walk | Stone | B5026 Eccleshall Road | Link Fway from 21 Ernald Gardens to 31 Ernald Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604313 | Link Fway | Stone | 21 Ernald Gardens | 31 Ernarld Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604267 | Link Fway | Stone | Friars Avenue | rear of 43 Ernald Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604314 | Link Fway | Stone | 55 Clinton Gardens | 45 Clinton Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604318 | Link Fway | Stone | 34 Friars Avenue | 42 Friars Avenue | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604315 | Link Fway | Stone | 57 Clinton Gardens | 67 Clinton Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604317 | Link Fway | Stone | 69 Downing Gardens | 69 Downing Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604316 | Tannery Walk | Stone | Downing Gardens | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604320 | Link Fway | Stone | at side of 46 Friars Avenue | at side of 46 Friars Avenue | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604319 | Link Fway | Stone | 12 Austin Close | 22 Austin Close | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604268 | Link Fway | Stone | Tiling Drive | Runnymede (Footbridge) | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601490 | Beacon Rise | Stone | Tiling Drive | Pirehill Lane | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601603 | Hill Drive | Stone | Beacon Rise | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601266 | Hill Crescent | Stone | Hill Drive | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601435 | Spring Gardens | Stone | Beacon Rise | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601612 | Heath Gardens | Stone | Beacon Rise | ends | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604286 | Link Fway | Stone | Pirehill Lane | Spring Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604288 | Link Fway | Stone | Wood Lane | link Fway Pirehill Lane to Spring Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604289 | Link Fway | Stone | 32 Heath Gardens | link Fway Pirehill Lane to Spring Gardens | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604287 | Link Fway | Stone | Heath Gardens | link Fway Pirehill Lane to Spring Gardens | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601490 | Wood Lane | Stone | Pirehill Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
D2413 | W1 | North | 37601198 | Wood Grove | Stone | Wood Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604290 | Link Fway | Stone | Beacon Rise | Hill Grove | Footway Preventative Treatment | Spring / Summer | Complete
D2136 | W1 | North | 37601490 | Pirehill Lane | Stone | B5026 Eccleshall Road | 156 Pirehill Lane | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601758 | Bankside | Stone | B5026 Eccleshall Road | Common Lane | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601538 | Meadow Way | Stone | Pirehill Lane | Common Lane | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601684 | Croft Road | Stone | Meadow Way | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601275 | Lea Road | Stone | Meadow Way | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601407 | Stuart Close North | Stone | Meadow Way | ends | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604264 | Link Fway | Stone | Meadow Way | Lea Road | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604263 | Link Fway | Stone | Meadow Way | Croft Road | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601556 | Marlborough Road | Stone | Pirehill Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601119 | Tudor Close | Stone | Marlborough Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37600971 | Stuart Close | Stone | Marlborough Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601598 | Highlands | Stone | Marlborough Road | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604265 | Link Fway | Stone | Redfern Road | Marlborough Road | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601660 | Essex Drive | Stone | Marlborough Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601336 | Windsor Close | Stone | Essex Drive | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601477 | Redfern Road | Stone | Pirehill Lane | Essex Drive | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37600973 | Goodill Close | Stone | Redfern Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601652 | Fraser Close | Stone | Redfern Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37600972 | Dutton Way | Stone | Redfern Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601704 | Coombe Park Road | Stone | Pirehill Lane | ends | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601609 | Hawthorn Avenue | Stone | Coombe Park Road | ends | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37602044 | Boundary Close | Stone | Coombe Park Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601104 | Cherry Tree Close | Stone | Coombe Park Road | ends | Footway Preventative Treatment | Spring / Summer | Complete
D2135 | W1 | North | 37601308 | Common Lane | Stone | B5026 Eccleshall Road | Approx 50m West of Crestwood Drive | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601720 | Bushberry Close | Stone | Common Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
D2414 | W1 | North | 37601050 | Foxwood Close | Stone | Common Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604261 | Link Fway | Stone | Common Lane | Birchfields Close | Footway Preventative Treatment | Spring / Summer | Complete
D2452 | W1 | North | 37601311 | Crestwood Drive | Stone | Common Lane | end | Footway Preventative Treatment | Spring / Summer | Complete
D2452 | W1 | North | 37601748 | Birchfields Close | Stone | Crestwood Drive | end | Footway Preventative Treatment | Spring / Summer | Complete
D2452 | W1 | North | 37601511 | Newlands Close | Stone | Crestwood Drive | end | Footway Preventative Treatment | Spring / Summer | Complete
D2452 | W1 | North | 37601579 | Lansdowne Close | Stone | Crestwood Drive | end | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | W1 | North | 37604262 | Link Fway | Stone | Birchfields Close | Newlands Close | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700503 | Junction Road | Leek | A520 Cheddleton Road | A53 Broad Street | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37701058 | Cornhill Gardens | Leek | Junction Road | ends | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700416 | Glebeville | Leek | Junction Road | ends | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700936 | Sandon Street | Leek | Junction Road | end | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700907 | Selborne Road | Leek | Junction Road | A520 Compton | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37701251 | Wardle Crescent | Leek | Selborne Road | Selborne Road | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700881 | Whitfield Street | Leek | Selborne Road | Junction Road | Footway Preventative Treatment | Spring / Summer | Complete
D1290 | N2 | North | 37700272 | Challinor Avenue | Leek | Selborne Road | Selborne Road | Footway Preventative Treatment | Spring / Summer | Complete
Div Fway | N2 | North | 37701658 | Hartington Close | Leek | Whitfield Street | Challinor Avenue | Footway Preventative Treatment | Spring / Summer | Complete
D3002 / D3556 | E3 | South | 23400709 / 23400028 | Barley Green Lane / Croxall Road (Old Road) | Alrewas | A515 Croxall Road RAB | Quarry entrance | Footway Preventative Treatment | Spring / Summer | Complete
D3212 | E2 | South | 23401265 | Rugeley Road | Chase Terrace | Duke Road | High Street | Footway Preventative Treatment | Spring / Summer | Programmed
C0146 | E2 | South | 23400137 | Chorley Road | Burntwood | Rugeley Road | Ogley Hay Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3404 | E2 | South | 23400458 | Lymington Road | Burntwood | Chorley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3404 | E2 | South | 23400424 | Sandown Close | Burntwood | Lymington Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3344 | E2 | South | 23400661 | The Crescent | Burntwood | Chorley Road | Chorley Road | Footway Preventative Treatment | Spring / Summer | Complete
D3247 | E2 | South | 23401406 | Wesley Close | Burntwood | Chorley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3247 | E2 | South | 23400792 | North Street | Burntwood | Chorley Road | Spinney Lane | Footway Preventative Treatment | Spring / Summer | Complete
D3546 | E2 | South | 23400696 | Squirrells Hollow | Burntwood | Chorley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3247 | E2 | South | 23400948 | Bells Lane | Burntwood | Chorley Road | Spinney Lane | Footway Preventative Treatment | Spring / Summer | Complete
D3247 | E2 | South | 23400855 | Longfellow Road | Burntwood | Bells Lane | Oak Lane | Footway Preventative Treatment | Spring / Summer | Complete
D3247 | E2 | South | 23400198 | Byron Close | Burntwood | Longfellow Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3247 | E2 | South | 23400796 | Oak Lane | Burntwood | North Street | Ogley Hay Road | Footway Preventative Treatment | Spring / Summer | Complete
D3348 | E2 | South | 23400480 | Beaudesert | Burntwood | Oak Lane | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3348 | E2 | South | 23400518 | Common View | Burntwood | Beaudesert | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3348 | E2 | South | 23400178 | Shaw Drive | Burntwood | Beaudesert | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3312 | E2 | South | 23400089 | Acorn Close | Burntwood | Oak Lane | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400475 | Birch Terrace | Burntwood | Oak Lane | Spinney Lane | Footway Preventative Treatment | Spring / Summer | Complete
D3570 | E2 | South | 23401293 | Spinney Close | Burntwood | Spinney Lane | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3211 | E2 | South | 23400775 | Ogley Hay Road | Burntwood | Chorley Road | Slade Road | Footway Preventative Treatment | Spring / Summer | Complete
D3580 | E2 | South | 23401347 | Heath Way | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3152 | E2 | South | 23400416 | Rake Hill | Burntwood | Ogley Hay Road | Property : No.73 | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400401 | Shelley Road | Burntwood | Birch Terrace | Wordsworth Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401005 | Chaucer Drive | Burntwood | Shelley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400888 | Kipling Avenue | Burntwood | Shelley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400658 | Tennyson Aenue | Burntwood | Shelley Road | Birch Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400569 | Wordsworth Road | Burntwood | Shelley Road | Birch Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400083 | Masefield Close | Burntwood | Wordsworth Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401086 | Deal Avenue | Burntwood | Parkhill Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23401092 | Fernleigh Avenue | Burntwood | Parkhill Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400084 | Blenheim Road | Burntwood | Parkhill Road | Brackenhill Road | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400188 | Thornfield Crescent | Burntwood | Blenheim Road | Brackenhill Road | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400969 | Brackenhill Road | Burntwood | Thornfield Crescent | Slade Road | Footway Preventative Treatment | Spring / Summer | Complete
D3298 | E2 | South | 23400403 | Slade Road | Burntwood | Parkhill Road | Ogley Hay Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400744 | Redwood Drive | Burntwood | Linden Avenue | Slade Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400342 | Columbian Crescent | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400189 | Oregon Gardens | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400851 | Lombardy Grove | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401063 | Corsican Close | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400427 | Oaken Gardens | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400928 | Aspen Grove | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400085 | Linden Avenue | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400915 | Alden Hurst | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401015 | Californian Grove | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400945 | Beechen Grove | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401035 | Coppice Close | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400506 | Carlton Crescent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401075 | Cumberland Crescent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400190 | Stamford Crscent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400320 | Lambert Drive | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400457 | Lulworth Road | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400533 | Dursley Road | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400359 | Eastwood Avenue | Burntwood | Ashmead Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401023 | Clinton Crescent | Burntwood | Morley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400558 | Halston Road | Burntwood | Ashmead Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3211 | E2 | South | 23400775 | Ogley Hay Road | Burntwood | Slade Road | Morley Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400446 | Ogley Vale | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3571 | E2 | South | 23401765 | Morlings Drive | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4118 | W3 | South | 36700666 | Giggetty Lane | Wombourne | Common Road | Planks Lane | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701489 | Birch Hill Avenue | Wombourne | Giggetty Lane | Wood Hill Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701194 | Honeybourne Crescent | Wombourne | Birch Hill Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701318 | Elder Grove | Wombourne | Birch Hill Avenue | Brook Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701458 | Brook Road | Wombourne | Oakwood Gardens (Private) | Lamb Crescent | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36700771 | Wood Hill Drive | Wombourne | Giggetty Lane | Brook Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701321 | Elm Tree Close | Wombourne | Wood Hill Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701136 | Lilac Drive | Wombourne | Wood Hill Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36700024 | Woodhill Close | Wombourne | Wood Hill Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36700292 | Lamb Crescent | Wombourne | Wood Hill Drive | Brook Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36700803 | Westbrook Way | Wombourne | Lamb Crescent | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36700670 | Dingle Road | Wombourne | Lamb Crescent | Brook Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4186 | W3 | South | 36701359 | Cranwell Green | Wombourne | Lamb Crescent | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4125 | W3 | South | 36700990 | Planks Lane | Wombourne | Giggetty Lane | St. Brides Close | Footway Preventative Treatment | Spring / Summer | Programmed
D4200 | W3 | South | 36700956 | Sandringham Road | Wombourne | Giggetty Lane | Windsor Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4200 | W3 | South | 36700506 | Windsor Road | Wombourne | Giggetty Lane | Sandringham Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4200 | W3 | South | 36701160 | Kirkstone Crescent | Wombourne | Windsor Road | Bramber Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D4200 | W3 | South | 36701480 | Bramber Drive | Wombourne | Windsor Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701027 | Garden Street | Leek | West Street | Belle Vue | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700217 | Belle Vue | Leek | Albert Street | A523 Mill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701470 | Nunn Street | Leek | Garden Street | Byrom Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701473 | Gaunt Street | Leek | Nunn Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701231 | Byrom Street | Leek | Nunn Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700403 | Frith Street | Leek | Belle Vue Road | Alma Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700476 | Hillswood Avenue | Leek | Alma Street | Hillcrest | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37702028 | Abbey Wood Close | Leek | Hillswood Avenue | number 14 Abbey Wood Close | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700496 | Hillcrest | Leek | Hillswood Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701122 | Albert Street | Leek | West Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700700 | School Street | Leek | West Street | Albert Street | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704038 | Link Fway | Leek | Belle Vue Road | Mill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701690 | Moorhouse Street | Leek | A523 Ashbourne Road | Wood Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700718 | Southbank Street | Leek | Moorhouse Street | A520 Compton | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700867 | Wood Street | Leek | A523 Ashbourne Road | Moorhouse Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701022 | Grosvenor Street | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700966 | Moorfields | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700751 | Talbot Street | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700981 | Livingstone Street | Leek | Talbot Street | Leonard Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701465 | Leonard Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700712 | Shoobridge Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700984 | London Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700370 | Duke Street | Leek | A520 Compton | London Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700682 | Prospect Place | Leek | A520 Compton | Cornhill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701221 | Cornhill Street | Leek | Prospect Place | end | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704102 | Link Fway | Leek | Leonard Street | Talbot Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700958 | Novi Lane | Leek | A53 Buxton Road | Ball Haye Green | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700836 | Windsor Drive | Leek | Novi Lane | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701017 | Haregate Road | Leek | Windsor Drive | Ball Haye Green | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701245 | Ball Haye Green | Leek | Novi Lane | Ball Haye Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701686 | Ball Haye Road | Leek | Ball Haye Green | Fowlchurch Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700802 | Vicarage Road | Leek | Fowlchurch Road | Ball Haye Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700991 | Lancaster Avenue | Leek | Ball Haye Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700962 | Nelson Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700971 | Milk Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700948 | Prince Street | Leek | Ball Haye Green | A53 Buxton Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701816 | Hayes Close | Leek | Prince Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701762 | Pump Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701139 | Hall Avenue | Leek | Ball Haye Green | Milner Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700684 | Provost Place | Leek | Hall Avenue | Novi Lane | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700610 | Milner Terrace | Leek | Novi Lane | Carlton Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701766 | Haig Road | Leek | Milner Terrace | Milner Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701480 | Carlton Terrace | Leek | Prince Street | Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701481 | Beatty Road | Leek | Carlton Terrace | Carlton Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701483 | Weston Street | Leek | A53 Buxton Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700827 | Victoria Street | Leek | Weston Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701482 | Shaw Place | Leek | A53 Buxton Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700193 | Abbotts Road | Leek | A53 Buxton Road | Horsecroft Crescent | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700763 | The Crescent | Leek | Abbotts Road | Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700846 | Westminster Road (Inc cul de sac) | Leek | Abbotts Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701051 | Furmston Place | Leek | Westminster Road | ends | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700176 | Argles Road | Leek | Westminster Road | Haregate Road and Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700485 | Horsecroft Crescent | Leek | Abbotts Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700942 | Ramshaw View | Leek | Horsecroft Crescent | Queens Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701358 | Queens Drive | Leek | Horsecroft Crescent | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700656 | Princess Avenue | Leek | Queens Drive | Windsor Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700654 | Prince Charles Avenue | Leek | Princess Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700777 | Thorncliffe View | Leek | Princess Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701359 | Tittesworth Avenue | Leek | Haregate Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700949 | Priory Avenue | Leek | Haregate Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700301 | Churnet View | Leek | Haregate Road | ends | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700938 | Roche Avenue | Leek | Haregate Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704081 | Link Fway | Leek | Windsor Drive | Link Fway | Footway Preventative Treatment | Spring / Summer | Programmed