## Programme
Programme Name: |  |  | Carriageway Preventative Treatments - Pre-Patching Operations
Programme Reporting Period: |  |  | March 2025 - March 2026
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
|  |  |  | Start Point | Finish Point
A0444 | 12900286 | Stapenhill Road | Burton Upon Trent | A5189 St Peters Bridge Island | A0511 Junction | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0511 | 12900922 | Bridge Street | Tutbury | Tutbury Bypass | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5121 | 12900454 | Byrkley Street | Burton upon Trent | Waterloo Street | Derby Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5121 | 12901641 | Parkway | Burton upon Trent | A38 junction | U4038 Parkway | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5121 | 12900325 | Waterloo Street | Burton upon Trent | Wellington Street | Byrkley Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5121 | 12900331 | Wellington Road | Burton upon Trent | U4038 Parkway | B5017 Shobnall Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5121 | 12900442 | Wellington Street | Burton upon Trent | B5017 Shobnall Road | Byrkley Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5189 | 12900419 | Evershed Way | Burton upon Trent |  | B5018 Orchard St Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5189 | 12900233 | Orchard Street | Burton upon Trent | B5018 Orchard St Island | B5018 Branston Road Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5189 | 12900361 | Shobnall Road | Burton upon Trent | A5121 Wellington St Island | C0357 Anglesey Road Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5008 | 12900227 | Newton Road | Burton upon Trent | A0511 Junction | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5017 | 12900435 | New Street | Burton upon Trent | High Street RAB | B5018 Orchard Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5017 | 12900389, 12900120 | Henhurst Hill | Burton upon Trent | Postern Road | Recycling joint adjacent Oakley Grange | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900393 | Guild Street | Burton upon Trent | Horninglow Street | Station Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900319 | Union Street | Burton upon Trent | Station Street | New Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900233 | Orchard Street | Burton upon Trent | New Street | Evershed Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900455 | Branston Road | Burton upon Trent | A5189 Orchard Street | C0357 Anglesey Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5416 | 12900523 | Station Street | Burton upon Trent | Guild Street | Start of block paving at Worthington Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0018 | 12900922 | Bridge Street | Tutbury | Tutbury Bypass RAB | Lower High Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0196 | 12900875 | Hanbury Hill | Hanbury | Fauld Lane | Anslow Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0197 | 12901375 | Wood Lane | Hanbury | Anslow Road | Knightsfield Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0197 | 12900788 | Wood Lane | Six Roads End | Knightsfield Road | Lichfield Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0240 | 12900363 | Rolleston Road Jct | Burton upon Trent | Bitham Lane junction | Harehedge Lane junction | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0359 | 12900182 | Main Street | Burton upon Trent | A444 St. Peters Street RAB | Hill Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0359 | 12900524 | Rosliston Road | Burton upon Trent | Hill Street | County boundary nr Walton Rd | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3439 | 12900849 | Martins Lane | Hanbury | Property : No.10 Martin Lane | Anslow Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3439 | 12900974 | Church Lane | Hanbury | Martins Lane | Property : The Thatches | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3458 | 12900832 | Nankirk Lane | Anslow Gate | Hanbury Road | Chapel Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3458 | 12901378 | Chapel Lane | Anslow Gate | Nankirk Lane | Hopley Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3459 | 12900916 | Bell House Lane | Anslow Gate | Hanbury Road | Burton Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3467 | 12900898 | Cuckoo Cage Lane | Tatenhill | Tatenhill Common | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3468 | 12900773 | Chapel Lane | Rangemore | Tatenhill Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3468 | 12900876 | Dingle Farm Lane | Rangemore | Tatenhill Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3469 | 12900854 | Highlands Park Lane | Tatenhill | Tatenhill Common | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3539 | 12900836 | Oakfields | Hanbury | Hanbury Hill | Meadow View Close (Private) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4001 | 12900380 | Lichfield Street | Burton upon Trent | A5189 Orchard Street | High Street RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4001 | 12900167 | High Street | Burton upon Trent | Worthington Way | Bridge Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4005 | 12900042 | Belvedere Road | Burton upon Trent | Calais Road | Dallow Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4005 | 12900473 | Dallow Street | Burton upon Trent | Belvedere Road | Horninglow Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4006 | 12900303 | Victoria Street | Burton upon Trent | Dallow Street | Derby Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4008 | 12900541 | Calais Road | Burton upon Trent | Charnwood Road (Nr surfacing joint) | Belvedere Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900051 | Castle Park Road | Burton upon Trent | Tutbury Road | Hornbrook Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900495 | Central Way | Burton upon Trent | Castle Park Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900134 | Farm Close | Burton upon Trent | Castle Park Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900548 | Green Lane | Burton upon Trent | Farm Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900153 | Hornbrook Road | Burton upon Trent | St. Andrew's Drive | Farm Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900496 | Hornbrook Close | Burton upon Trent | Hornbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900449 | St. Andrew's Drive | Burton upon Trent | Hornbrook Road | Rolleston Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900300 | St. Martin's Close | Burton upon Trent | St. Andrew's Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900272 | St. Aidan's Close | Burton upon Trent | St. Andrew's Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900243 | Poplars Road | Burton upon Trent | Hornbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900176 | Hornton Road | Burton upon Trent | Hornbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900135 | Farm Road | Burton upon Trent | Horninglow Road North | Hornbrook Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12901612 | Ivy Grove | Burton upon Trent | Rolleston Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900408 | Harper Avenue | Horninglow | Horninglow Road North | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900274 | St.Francis Close | Horninglow | Harper Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900497 | St.Davids Drive | Horninglow | Harper Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900282 | St.Patricks Road | Horninglow | Harper Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4009 | 12900354 | St.Michaels Road | Horninglow | Harper Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0454 | 23401800 | Aldridge Road | Aldridge | Little Aston Road | Aldridge Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0454 | 23400249 | Aldridge Road | Little Aston | Aldridge Road | Walsall Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0454 | 23401801 | Little Aston Road | Aldridge | A452 Chester Road | Aldridge Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0461 | 23401840 | Falkland Road | Lichfield | Sainte Foy Avenue | A5127 Birmingham Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0461 | 23410182 | Limburg Avenue | Lichfield | Walsall Road | Sainte Foy Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0461 | 23401615 | Sainte Foy Avenue | Lichfield | Limburg Avenue | The Friary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0461 | 23400604, 23400382 | Walsall Road | Lichfield | A5190 Lichfield Rd (joint with recent junct imps) | Limburg Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 23400922 | Armitage Road | Armitage | Leahall Way Island | Hawkesyard Estate entrance | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 23400299 | Rugeley Road | Armitage | Hawkesyard Estate entrance | Old Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 23400812 | New Road | Armitage | Old Road | The Green | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 23400148 | Kings Bromley Lane | Handsacre | A0515 Lichfield Road | Nature Reserve entrance | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 23400732 | Rugeley Road | Handsacre | Nature Reserve entrance | B5014 Uttoxeter Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A4026 | 23400870 | Little Aston Lane | Little Aston | Walsall Road | Blake Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23400499 | Church Street | Lichfield | C0353 Greenhill (construction joint) | Near hospital entrance (construction joint) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23401249 | Trent Valley Road | Lichfield | Near Wissage Road (construction joint) | Eastern Avenue Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23401249 | Trent Valley Road | Lichfield | Eastern Avenue Island | Railway Bridge | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23401753 | Burton Road | Lichfield | Railway Bridge | Property : Ebrook Clinic (construction joint) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23400954 | Birmingham Road | Wall | A5 Watling Street | Knowle Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A5127 | 23400231 | Birmingham Road | Lichfield | Knowle Lane | Sainte Foy Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B4138 | 2709161, 23400421 | Rosemary Hill Road | Little Aston | Park Drive | Blake Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B4138 | 23400628 | Thornhill Road | Streetly | County Boundary(Foley Rd East) | C0011 Hardwick Road RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0176 | 23400818 | Mill Lane | Mill Green | A452 Chester Road | A0454 Aldridge Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0306 | 23400231 | Birmingham Road | Lichfield | The Friary | Upper John Street Jct (construction joint) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0352 |  | Bird Street | Lichfield | No.1 Beacon Road | Minister Pool Walk | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3068 | 23400653 | Talbot Avenue | Streetly | Little Aston Park Road | Property - Westgate House | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3068 | 23400788 | Newick Avenue | Streetly | Little Aston Park Road | Talbot Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3068 | 23400453 | Little Aston Park Road | Streetly | Hardwick Road | Newick Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0051 | 39400209 | Dosthill Road | Two Gates | B5404 Watling Street | Tamworth Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0051 | 39400241 | Tamworth Road | Dosthill | Dosthill Road | Hedging Lane Surfacing Joint | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0051 | 39400626 | High Street | Dosthill | Hedging Lane Surfacing Joint | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 39400346 | Offa Drive | Tamworth | B5493 Upper Gungate (construction joint) | Albert Road Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 39400094 | Saxon Drive | Tamworth | Albert Road Island | Bolebridge Street Isalnd | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A4091 | 23400501, 23400230 | Coleshill Road | Fazeley / Drayton Bassett | Brook End (construction joint) | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5404 | 23401327 | Watling Street | Mile Oak | A453 Sutton Road Crossroads | Brewster Close | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5404 | 23401328 | Lichfield Street | Fazeley | Brewster Close | A4091 Tamworth Road Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0282 | 23401286 | The Beck | Elford | The Shrubbery | Burton Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0282 | 23400647 | The Shrubbery | Elford | Burton Road | The Beck | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0370 | 39400557 | Coton Lane | Tamworth | Fotenaye Road (construction joint) | A51 Fox Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D3556 | 23400028 | Croxall Road (Old Road) | Alrewas | Barley Green Lane (Quarry entrance) | Just short of the railway crossing | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400658 | Leyland Road | Tamworth | Marlborough Way | Marlborough Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400454 | Dumolo's Lane | Tamworth | Glascote Lane | Leyland Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400179 | Wyvern | Tamworth | Dumolo's Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39401006 | Lychgate Close | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400452 | Sunbeam | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400082 | Riley | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400016 | Lotus | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400300 | Lagonda | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400664 | Jowett | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400188 | Jensen | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400635 | Jaguar | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400189 | Healey | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400453 | Cowley | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400482 | Belsize | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400478 | Allard | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400235 | Wolseley | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400237 | Trojan | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400161 | Triumph | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400391 | Talbot | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400247 | Swift | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400789 | Napier | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400649 | Hillman | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U6041 | 39400568 | Dennis | Tamworth | Leyland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0138 | 37601816 | High Street | Church Eaton | Little Onn Road | Common Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0139 | 37601078 | Cowley Lane | Gnosall | Wharf Road | Broad Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0139 | 37601948 | Church Eaton Road | Church Eaton | Cowley Lane | Broad Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0139 | 37602278 | Malthouse Lane | Church Eaton | Broad Lane | High Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0229 | 37601871 | Gnosal Lane | Moreton | County Boundary (Near Moreton Brook bridge) | Post Office Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0229 | 37601829 | Church Eaton Road | Bromstead | Post Office Lane | Orslow Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0229 | 37601797 | Church Eaton Road | High Onn | Orslow Road | Little Onn Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0297 | 37601801 | Gorsemoor Lane | Church Eaton | Broad Lane | Orlsow Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2352 | 37601303 | Ginger Hill | Gnosall | Cowley Lane | Wharf Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2352 | 37601651 | Fountain Fold | Gnosall | Ginger Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2352 | 37601242 | Nearridding | Gnosall | Ginger Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2352 | 37601663 | Far Ridding | Gnosall | Ginger Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4568 | 37601835 | Wood Eaton Road | Church Eaton | Malthouse Lane | High Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0460 | 5500862 | Horse Fair | Rugeley | Globe Island | Breton Road / Armitage Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0513 | 5500591, 5501442 | Armitage Road | Rugeley | Brereton Road | A51 Lea Hall Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5017 | 5500462 | Norton Hall Lane | Cannock | Washbrook Lane | Property : No.17 Norton Hall Lane (Surfacing Joint) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5019 | 5500511 | Burntwood Road | Norton Canes | A5190 Cannock Road Island | Property : Library (Surf Joint) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5020 | 5500980 | Norton East Road | Norton Canes | Burntwood Road | Brownhills Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500108 | School Road | Norton Canes | Burntwood Road | Norton East Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500452 | Poplar Street | Norton Canes | Brownhills Road | School Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5501082 | Railway Street | Norton Canes | Brownhills Road | School Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5501083 | School Crescent | Norton Canes | School Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500107 | School Close | Norton Canes | School Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500895 | Lakeside Drive | Norton Canes | Stag Crescent | Norton East Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500538 | Stag Crescent | Norton Canes | Burntwood Road | Lakeside Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5501058 | Grange Road | Norton Canes | Lakeside Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500757 | Deer Close | Norton Canes | Burntwood Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500051 | Park Road | Norton Canes | Brownhills Road | Norton East Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500049 | Park Avenue | Norton Canes | Brownhills Road | Park Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5043 | 5500907 | Legion Close | Norton Canes | Burntwood Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500636 | Breeze Avenue | Norton Canes | Norton East Road | St.James Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500984 | Pool Avenue | Norton Canes | Breeze Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500146 | St.James Road | Norton Canes | Breeze Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500316 | High Street | Norton Canes | Norton East Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500122 | Silver Birch Road | Norton Canes | High Street | Cherry Tree Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500713 | Cherry Tree Road | Norton Canes | High Street | Brownhills Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5044 | 5500798 | Elm Road | Norton Canes | High Street | Cherry Tree Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5088 | 5500552 | Pump Lane | Rugeley | Bower Lane | Property : No.1 Finches Hill | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5088 | 5500809 | Finches Hill | Rugeley | Pump Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5088 | 5500743 | Crestwood Rise | Rugeley | Bower Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5088 | 5501103 | Whitworth Lane | Rugeley | Church Lane | Peakes Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500920 | Lovett Court | Rugeley | Winstanley Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501460 | Winstanley Close | Rugeley | School Road | Lovett Court | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501287 | School Road | Rugeley | Plovers Rise | Fernwood Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501132 | Fernwood Drive | Rugeley | Plovers Rise | School Road / Private Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501131 | Park Hall Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500232 | Watson Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501130 | Jeffery Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500819 | Grindcobbe Grove | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501286 | Tyler Way | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500528 | Wat Tyler Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500133 | Springfield Road (Side Roads x 2) | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500874 | John Ball Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500830 | Harney Court | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500379 | William Morris Court | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500379 | Oak Close | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500293 | Hollyoake Place | Rugeley | Springfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501283 | Jennie Lee Way | Rugeley | Springfield Road | Aneurin Bevan Place | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501105 | Aneurin Bevan Place | Rugeley | Jennie Lee Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500683 | Byron Place | Rugeley | Jennie Lee Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500754 | Daywell Rise | Rugeley | Bower Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500686 | Cambrian Lane | Rugeley | Bower Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5500229 | Winstanley Place | Rugeley | Winstanley Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5089 | 5501284 | Byron Close | Rugeley | Jennie Lee Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5111 | 5501406 | Voyager Drive | Cannock | Eastern Way Island | Orbital Way Iskand | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5111 | 5501323 | Orbital Way | Cannock | Eastern Way Island | Gemini Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5111 | 5501488 | Gemini Way | Cannock | Orbital Way | Morston Court | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5111 | 5501492 | Blakeney Way | Cannock | Morston Court | Washbrook Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U5111 | 5500230 | Washbrook Lane | Cannock | Blakeney Way | A5 Watling Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B4176 | 36701466 | Long Common | Claverley | B4176 Bridgnorth Road / Tom Lane junction | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0006 | 36700035 | Harriotts Hayes Lane | Codsall Wood | C0006 Wood Road | District Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0006 | 36700181 | Wood Lane | Codsall Wood | Near Pendrell Hall | Slate Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0006 | 36700356 | Wood Lane | Codsall | Slate Lane | Near Bakers Gardens | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0006 | 36701528 | Bakers Way | Codsall | Near Bakers Gardens | Wolverhampton Road Island | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0050 | 36700826 | Upper Landywood Lane | Great Wyrley | Landywood Lane | Strawberry Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0051 | 36700377 | Strawberry Lane | Great Wyrley | Streets Lane | New Landywood Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0051 | 36701025 | Old Landywood Lane | Essington | New Landywood Lane | Warstone Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0078 | 36701469, 36700380 | Pool House Road | Wombourne | B4176 Bridgnorth Road | Clap Gate Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0078 | 36701011 | Ounsdale Road | Wombourne | Clap Gate Road | Station Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0078 | 36700186 | School Road | Wombourne | Station Road | Billy Buns Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0217 | 36701036 | Oaken Lane (Cut Thro') | Codsall | Oakens Lane | Histons Hill | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36701419 | Chapel Lane | Codsall | Station Road | Histons Hill | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36700863 | Broadway | Codsall | Chapel Lane | Broadway | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36700613 | Long Acre | Codsall | Broadway | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36700627 | Lansdowne Avenue | Codsall | Station Road | Chapel Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36700975 | Queens Gardens | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4034 | 36701158 | Kingsley Gardens | Codsall | Oakens Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4143 | 36700166 | Lane Green Road | Codsall | Duck Lane | Birches Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4165 | 36700399 | Palmers Way | Codsall | Lane Green Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4165 | 36700289 | Palmers Close | Codsall | Palmers Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4178 | 36700739 | Birches Park Road | Codsall | Keepers Lane | Parkes Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4178 | 36700616 | Mardeira Avenue | Codsall | Birches Park Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4178 | 36700577 | Parkes Avenue | Codsall | Birches Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4178 | 36700422 | Kynaston Crescent | Codsall | Parkes Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4183 | 36700291 | Heath Farm Road | Codsall | Wesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4185 | 36700848 | The Paddock | Codsall | Suckling Green Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4185 | 36700809 | Wayside Acres | Codsall | Suckling Green Lane | Property: No.20 | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4185 | 36701752 | Farway Gardens | Codsall | Suckling Green Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4187 | 36701420 | Charters Avenue | Codsall | Birches Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700500 | Wesley Road | Codsall | Duck Lane | Lane Green Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36701307 | Farm Close | Codsall | Wesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700146 | Green Oak Road | Codsall | Wesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700783 | Whitefield Close | Codsall | Wesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700799 | Wesley Avenue | Codsall | Wesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36701037 | Oakfield Road | Codsall | Wesley Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700384 | Ringhills Road | Codsall | Wesley Road | Wesley Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36701246 | Hatons Grove | Codsall | Ringhills Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36701456 | Brook Grove | Codsall | Ringhills Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4188 | 36700293 | Woodside Grove | Codsall | Ringhills Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4195 | 36700279 | Princess Gardens | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4195 | 36700973 | Princess Drive | Codsall | Princess Gardens | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4195 | 36701208 | Histons Drive | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4204 | 36701490 | Birches Avenue | Codsall | Birches Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4214 | 36700328 | Meadow Way | Codsall | Oakens Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4218 | 36700704 | Brookfield Road | Codsall | Duck Lane | Lane Green Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4247 | 36701496 | Beech Gardens | Codsall | Suckling Green Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4253 | 36701408 | Chestnut Close | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4253 | 36700329 | Poplars Drive | Codsall | Suckling Green Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4261 | 36700563 | Red Rock Drive | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4268 | 36701486 | Bilbrook Grove | Codsall | Duck Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4367 | 36700651 | Hatherton Street | Cheslyn Hay | Hill Street | High Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4367 | 36701222 | Hill Street | Cheslyn Hay | Wolverhampton Road | Pinfold Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4370 | 36700544 | Rosemary Road | Cheslyn Hay | Low Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4372 | 36701018 | Park Street | Cheslyn Hay | Station Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4373 | 36700542 | Streets Lane | Great Wyrley | Landywood Lane | Strawberry Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4414 | 36701374 | Coppice Lane | Cheslyn Hay | Hawkins Drive Island | Station Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4453 | 36700776 | Windsor Road | Cheslyn Hay | Littlewood Lane | Littlewood Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4453 | 36700754 | Woodland Drive | Cheslyn Hay | Windsor Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4464 | 36701889 | Besom Way | Cheslyn Hay | Pinfold Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4464 | 36700987 | Pinfold Lane | Cheslyn Hay | High Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700802 | Westbourne Avenue | Cheslyn Hay | Station Street | Sutherland Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700448 | Frensham Close | Cheslyn Hay | Westbourne Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701682 | Peace Close | Cheslyn Hay | Westbourne Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701029 | Orchard Close | Cheslyn Hay | Westbourne Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701263 | Glenthorne Drive | Cheslyn Hay | Westbourne Avenue | New Horse Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700102 | Tudor Close | Cheslyn Hay | Glenthorne Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701110 | Magna Close | Cheslyn Hay | Glenthorne Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701015 | Park Close | Cheslyn Hay | Glenthorne Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700250 | Tennscore Avenue | Cheslyn Hay | Glenthorne Drive | Sutherland Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700381 | Quarry Close | Cheslyn Hay | Tennscore Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700100 | Sutherland Road | Cheslyn Hay | Glenthorne Drive | Landywood Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700930 | Short Lane | Cheslyn Hay | Sutherland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700714 | Chase Avenue | Cheslyn Hay | Sutherland Road | Berwyn Grove | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36701505 | Berwyn Grove | Cheslyn Hay | Chase Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700608 | Leveson Avenue | Cheslyn Hay | New Horse Road | Sutherland Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700101 | Mount Close | Cheslyn Hay | Sutherland Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700585 | New Horse Road | Cheslyn Hay | Station Street | Sutherland Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700323 | Sandown Avenue | Cheslyn Hay | New Horse Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4468 | 36700583 | Mount Pleasant | Cheslyn Hay | New Horse Road | Property : No.15 | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36701540 | Anson Road | Great Wyrley | Landywood Lane | Gorsey Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700103 | Colinwood Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700979 | Ramillies Crescent | Great Wyrley | Anson Road | Anson Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700104 | Leander Close | Great Wyrley | Ramillies Crescent | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700105 | Orion Close | Great Wyrley | Ramillies Crescent | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700106 | Achilees Clolse | Great Wyrley | Ramillies Crescent | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700747 | Anson Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700574 | Oxley Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36700840 | Triton Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36701050 | Norfolk Grove | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36701279 | Frobisher Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4473 | 36701615 | Ajax Close | Great Wyrley | Anson Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4475 | 36700385 | Rosemary Avenue | Cheslyn Hay | Rosemary Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4489 | 36700460 | Coppice Close | Cheslyn Hay | Coppice Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4490 | 36700228 | Mitre Road | Cheslyn Hay | Pinfold Lane | High Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4490 | 36700229 | Campians Avenue | Cheslyn Hay | Mitre Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4497 | 36700230 | Fennel Close | Cheslyn Hay | Rosemary Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4511 | 36700774 | Windsor Gardens | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4513 | 36701102 | Meadow Vale | Codsall | Birches Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4516 | 36701125 | Lodge View | Cheslyn Hay | Saredon Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4516 | 36701384 | Clover Ridge | Cheslyn Hay | Low Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4522 | 36700712 | Cemetery Street | Cheslyn Hay | Wolverhampton Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4523 | 36700983 | Pine Walk | Codsall | Histons Hill | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4534 | 36701266 | Gorsty Hayes | Codsall | Wolverhampton Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4541 | 36700233 | Pendinas Drive | Codsall | Duck Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36700208 | Weston Drive | Great Wyrley | Streets Lane | Streets Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36700695 | Chillington Close | Great Wyrley | Weston Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36701312 | Dunston Close | Great Wyrley | Weston Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36700209 | Somerford Close | Great Wyrley | Weston Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36701001 | Pendrell Close | Great Wyrley | Dunston Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4555 | 36701331 | Dove Hollow | Great Wyrley | Streets Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4557 | 36701272 | Grassmere Court | Cheslyn Hay | Low Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4610 | 36701364 | Coltsfoot View | Cheslyn Hay | Landywood Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4610 | 36701083 | Merrill Close | Cheslyn Hay | Coltsfoot View | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D4654 | 36700428 | Green Acre Drive | Codsall | Birches Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4045 | 36702105 | Dam Hill Close | Codsall | Lane Green Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U4046 | 36702101 | The Spindles | Great Wyrley | Gorsey Lane | Property: Loom Close | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900065 | Burton Road | Burton upon Trent | C0357 Anglesey Road | U4017 Warren Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5018 | 12900004 | Main Street | Burton upon Trent | U4017 Warren Lane | A5121 Wellington Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0051 | 23401381, 5501424 | Leahall Way | Armitage | A0513 Armitage Road | A0051 Brereton Hill | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0522 | 37700800. 37701369,37700823 | Uttoxeter Road | Lower Tean/Checkley | C0251 Mill Lane | Leigh Lane (Lower Tean) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5027 | 12901007 | Stone Road/Bramshall Road | Uttoxeter | Approx 350m east of Stocks Lane | Byrds Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5031 | 12901261, 12901762, 12901833 | Main Road/New Road | Denstone | New Rd/Lady Meadow roundabout | B5032 Denstone Lane roundabout | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5031 | 12901266 | New Road | Rocester | B5030 Rocester Bypass roundabout | Lady Meadow Lane roundabout | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A34 | 27001142 | London Road | NUL | Stoke City coundary approx 80m south east of Hospital junction | Grosvenor/Brook Lane RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A34 | 27001747, 27001117 | Talke Road/Liverpool Road | Chesterton/Cross Heath | B5369 Wolstanton Road RAB | B5368 Milehouse Lane RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A34 | 27001117 | Liverpool Road | Cross Heath | B5367 Knutton Lane RAB | B5368 Milehouse Lane RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A519 | 27000692 | Clayton Road | NUL/Westbury Park | Northwood Lane RAB | Approx 10m north Nuffield Hospital access | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A519 | 27000692 | Clayton Road | NUL/Clayton | Kingsbridge Avenue | Stafford Avenue RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A52 | 27000679 | Brunswick Street | NUL | Borough Road | A52 Nelson Place RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A52 | 27000656 | George Street | NUL | Borough Road | Stoke City boundary approx 10m east of Albert Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A525 | 27001454, 27001527, 27001606, 27001541 | Newcastle Road/Poolside | Madeley Heath/Madeley | A531 Crewe Road | Manor Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A527 | 27000522, 27001030 | Brampton Rd/High Street | May Bank | Sandy Lane RAB | B5369 Basford Park Road junction | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A53 | 27001082 | King Street | NUL/Brampton | A52 Nelson Place RAB | Borough Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5026 | 27001451 | Mucklestone Road | Loggerheads | A53 Newcastle Road | 30/60mph speed limit approx 50m north Mucklestone Wood Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5368 | 27001310 | Milehouse Lane | NUL/Dimsdale | B5369 Alexandra Road | Hoon Avenue RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5369 | 27000722, 27000663, 27001220 | Alexandra Road/Dimsdale Parade East & West | NUL | A527 High Street junction | Hassam Parade | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5500 | 27001221, 27000205, 27000552 | Victoria Street/Red Lion Square | Chesterton/NUL | Approx 20m southwest Victoria Place | 30/40mph speed limit approx 65m northwest Church Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0061 | 27000723 | Alsager Road | NUL/Audley | B5500 Nantwich Road | Approx 50m south of A500 | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0362 | 27000991 | Hassell Street | NUL | A527 Barracks Road | Marsh Parade | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0363 | 27001141 | London Road | Chesterton | B5500 Victoria Street | Church Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0363 | 27001141 | Dragon Square | Chesterton/NUL | C0363 London Road | Approx 30m north of Rosevale Court | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2036 | 27001477 | Station Road | Onneley | A525 Woore Road | limit of adoption approx 1020m southeast | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2041 | 27001512 | Wilkinspleck | NUL/Limepits | Three Mile Lane | limit of adoption approx 330m northeast | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2104 | 27001550 | Stableford Bank | Chapel Chorlton | A51 The Rowe | D2103 Haddon Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001460 | John Offley Road | Madeley | Moss Road | Izaak Walton Way | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001552 | Morningside | Madeley | John Offley Road | John Offley Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001530 | Laverock Grove | Madeley | Morningside | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001553 | Birch Dale | Madeley | Morningside | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001414 | Cherry Hill | Madeley | Birch Dale | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001428 | Grayling Willows | Madeley | Cherry Hill | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001397 | Bramble Lea | Madeley | Cherry Hill | Morningside | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2213 | 27001532 | Merlin Green | Madeley | Cherry Hill | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2228 | 27001433 | Hillview Crescent | Baldwins Gate | Gatewy Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001577 | The Bridle Path | Madeley | Moss Lane | Beresford Dale | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001463 | Plover Field | Madeley | The Bridle Path | Charles Cotton Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001486 | Pear Tree Drive | Madeley | The Bridle Path | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001578 | Apple Croft | Madeley | The Bridle Path | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001520 | Primrose Dell | Madeley | Charles Cotton Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001430 | Heather Glade | Madeley | The Bridle Path | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001447 | Fern Dene | Madeley | The Bridle Path | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001411 | Beresford Dale | Madeley | Charles Cotton Drive | Charles Cotton Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2248 | 27001403 | Charles Cotton Drive | Madeley | Moss Lane | Primrose Dell | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2583 | 27001623 | River Lea Mews | Madeley | Moss Lane | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001785 | Beck Road | Madeley | A525 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001786 | Kingfisher Close | Madeley | Beck Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001789 | Heron Close | Madeley | Beck Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001789 | Salisbury Close | Madeley | Beck Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001787 | Elkington Rise | Madeley | Salisbury Close | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2585 | 27001788 | Daltry Way | Madeley | Salisbury Close | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2595 | 27001704 | Fairgreen Road (Inc cul de sac) | Baldwins Gate | A53 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2005 | 27000829 | Church Bank | NUL/Audley | Church Street | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2011 | 27000894 | Dean Hollow | NUL/Audley | Chester Road | Church Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2021 | 27001622 | Barleyfields | NUL/Audley | Meadowside Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2027 | 27000427 | Wilbrahams Walk | NUL/Audley | B5500 Nantwich Road | Church Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2031 | 27000985 | Hardingswood Road | NUL/Kidsgrove | A50 Liverpool Road | Second Avenue (railway bridge) | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2039 | 27000284 | Spey Drive (Inc all cul de sacs) | NUL/Kidsgrove | Mount Road | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2039 | 27001249 | Mount Road | NUL/Kidsgrove | Whitemill Road RAB | A50 Kidsgrove Bank | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2047 | 27001252 | Ian Road | NUL/Kidsgrove | Pennyfields Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2057 | 27001262 | Church Street | Chesterton | B5500 Audley Road | C363 London Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2060 | 27000086 | Meadow Lane | NUL/Cross Heath | B5368 Lower Milehouse Lane | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2060 | 27001127 | Lovatt Avenue | NUL/Cross Heath | Meadow Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2060 | 27000356 | Thomas Avenue | NUL/Cross Heath | Meadow Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2060 | 27000470 | Johnson Avenue | NUL/Cross Heath | Meadow Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2060 | 27001209 | Meadow Lane | NUL/Cross Heath | Meadow Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2067 | 27000811 | Cemetery Road | Silverdale | A525 Keele Road RAB | B5044 Silverdale Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2069 | 27000978 | Gallows Tree Lane | NUL/Thistleberry | A525 Keele Road RAB | Sneyd Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2069 | 27000592 | Sneyd Avenue | NUL/Westlands | A53 Whitmore Road RAB | Gallows Tree Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2074 | 27000156 | Northwod Lane | NUL/Northwood | A519 Clayton Road RAB | Northwood Close | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2075 | 27000303, 27000509 | Stafford Avenue/Clayton Lane | NUL/Clayton | A519 Clayton Road RAB | Stoke City boundary approx 10m northeast of Lyme Brook bridge | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2079 | 27000751 | Boundary Street | NUL | A52 George Street | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2080 | 27000703 | Borough Road | NUL | A53 King Street | A52 George Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000760 | Bentley Avenue | NUL | B5368 Milehouse Lane | Hollinshead Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000646 | Hollinshead Avenue | NUL | Hassam Parade | Brant Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000781 | Brant Avenue | NUL | Harper Avenue | Hollinshead Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000876 | Coppice View | NUL | Brant Avenue | Hollinshead Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000482 | Harper Avenue | NUL | Bentley Avenue | Brant Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27000256 | Saunders Road | NUL | B5368 Milehouse Lane | Hollinshead Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
U2093 | 27001311 | Quinton Grove | NUL | Bentley Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0053 | 37700517, 37700986 | Leek Road/Ladderedge | Longsdon/Leek | Approx 65m east of City Lane | approx 250m southwest of School Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0520 | 37700920 | St Edwards Street | Leek | A53 Brook Street | A523 Church Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0520 | 37700907, 37700260 | Compton/Cheddleton Road | Leek | A53 Brook Street | Junction Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0520 | 37700260 | Cheddleton Road | Leek | Junction Road | Co-op/Brittania Building RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0520 | 37701923, 37700528 | Cheddleton Rd/Leek Rd | Leekbrook/Cheddleton Heath | Sheephouse Farm access | Brambling House access approx 190m southwest of Wardle Gardens | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0521 | 37701209 | Froghall Road | Cheadle | A522 Leek Road | Shawpark Farm access | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0522 | 37702170 | Cheadle Road | Consall | A520 Main Road | A52 Blakeley Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0522 | 37700779 | Tean Road | Cheadle/Mobberley | Freehay Road | approx Eaves Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0527 | 37701963, 37701964 | Macclesfield Road | Leek/Rudyard | Approx 50m north B5331 Rudyard Road | Churnet Way/Sainsburys RAB | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0527 | 37701964, 37701965, 37701960 | Macclesfield Road/Mill Street | Leek | Churnet Way/Sainsburys RAB | A520 St Edwards Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
A0527 | 37702106 | Tunstall Road | Knypersley | Stoke City boundary | Brown Lees Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5053 | 37700091 | Onecote Road | Bottom House | A523 Ashbourne Road | C0004 Morridge Top Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
B5054 | 37700579, 37700578 | New Road/Mill Lane | Warslow/Hulme End | Approx 700m east B5053 | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0054 | 37700495 | Ilam Moor Lane | Ilam | Brunnister Lane | C55 Blore Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0054 | 37700019 | Thorpe Road | Dove Dale | C55 Blore Road | County Boundary | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0055 | 37700099 | Blore Road | Ilam | C54 Thorpe Road | C56 Yerley Hill | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0056 | 37701752 | Blore Lane | Calton Moor | A52 Ashbourne Road | C55 Blore Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0068 | 37700793, 37701215, 37701792 | The Hollow/Dilhorne Rd/Caverswall Rd | Caverswall/Dilhorne | C191 Blythe Bridge Road | D1180 Dilhorne Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0109 | 37701007, 37701040, 37700367 | Draycott Road/High Street | Totmonslow/Upper Tean | Approx 50m east Riverside Road | Approx 30m west Breach Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0150 | 37700628 | Ostlers Lane | Cheddleton | Hollow Lane | A520 Cheadle Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
C0355 | 37701173 | Park Lane | Knypersley | A527 Tunstall Road | Mill Hayes Road roundabout | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1050 | 37700404, 37701401 | Shawfields/Swallow Moss | Shawfield/Blakemere | C22 Middlehills | D1096 Newtown Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1058 | 37700757, 37702114 | Stanley Moss Road/Lane | Stanley | C186 Stanley Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1077 | 37701764 | Victoria Row | Knypersley | A527 Tunstall Road | end at rear of houses | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1087 | 37700699 | Douse Lane | Onecote | C4 Morridge Top Road | B5053 Onecote Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1092 | 37700973, 37701758 | Millmoor Head | Blakemere/Shawfield | C22 Middlehills | D1096 Shawfield Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1107 | 37700149 | Hollow Lane | Cheddleton | A520 Cheadle Road | C150 Ostlers Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1143 | 37701166 | School Drive | Oakamoor | Carr Bank | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1143 | 37700300 | Churnet View Road | Oakamoor | School Drive | limit of adoption approx 390m west | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1239 | 37701127 | Ash Grove | Werrington | A52 Ash Bank Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700360 | Dorset Drive | Biddulph | A527 Meadows Way | Station Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37701196 | Hunters Close (Inc cul de sac) | Biddulph | Dorset Drive | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700785 | Thatcher Grove | Biddulph | Dorset Drive | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37701329 | Mason Drive | Biddulph | Dorset Drive | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700325 | Crofters Close | Biddulph | Dorset Drive | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700316 | Coopers Way | Biddulph | Dorset Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37701035 | Forrester Close | Biddulph | Dorset Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700692 | Sawyer Drive | Biddulph | Dorset Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37701451 | Potters End | Biddulph | Sawyer Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700616 | Norfolk Grove | Biddulph | Dorset Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37701330 | Devon Grove | Biddulph | Dorset Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700570 | Meadowside | Biddulph/Knypersley | Newpool Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1279 | 37700386 | Gas Works Road | Biddulph | Station Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1280 | 37700321 | Coronation Avenue | Knypersley | A527 Tunstall Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1282 | 37700169 | Baileys Bank | Biddulph | A527 Congleton Road | Approx 125m west of A527 Congleton Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1282 | 37700169 | Baileys Bank | Biddulph | Marsh Green Road | Approx 130m north of Marsh Green Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37700309 | Colwyn Drive | Knypersley/Biddulph | Mill Hayes Road | Orme Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37700597 | Menai Drive | Knypersley/Biddulph | Colwyn Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37701023 | Gwyn Avenue | Knypersley/Biddulph | Colwyn Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37700602 | Nevin Avenue | Knypersley/Biddulph | Colwyn Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37700626 | Orme Road | Knypersley/Biddulph | Mill Hayes Road | approx 290m north Mill Hayes Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37700443 | Harlech Drive | Knypersley/Biddulph | Conway Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37701217 | Denbigh Close | Knypersley/Biddulph | Harlech Drive | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37701456 | Conway Road (service road) | Knypersley/Biddulph | Conway Road | Conway Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1283 | 37704022 | Access between Conway Road service road and Park Lane | Knypersley/Biddulph | Conway Road service road | Park Lane | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1284 | 37700525 | Lawton Street | Biddulph | C0005 Congleton Road | St Johns Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1284 | 37700318 | Coppice Close | Biddulph | St Johns Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1284 | 37701118 | William Avenue | Biddulph | St Johns Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1284 | 37700620 | Oakdene Way | Biddulph | William Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1288 | 37700648 | Organ Ground | Leek | Shirburn Road | approx 80m east | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1288 | 37701053 | Cross Street | Leek | A523 Ashbourne Road | approx 70m north east | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1289 | 37701690 | Moorhouse Street | Leek | A523 Ashbourne Road | Southbank Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1289 | 37700718 | Southbank Street | Leek | Moorhouse Street | A520 Compton | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1290 | 37701374 | Barnfield Road | Leek | A53 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1290 | 37701246 | Barnfields Close | Leek | Barnfields Road | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1290 | 37700773 | Sunnyhills Road | Leek | Barnfields Road | A53 Newcastle Road | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1291 | 37701219 | Cruso Street | Leek | A53 Broad Street | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1291 | 37701469 | Grove Street | Leek | West Street | Westwood Grove | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1291 | 37700862 | Westwood Grove | Leek | Grove Street | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1291 | 37700502 | Jubilee Terrace | Leek | Grove Street | North Street | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1292 | 37704171 | The Doves | Leek | Haregate Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1292 | 37704169 | Osprey Close | Leek | Haregate Road | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700596 | Meigh Road | Werrington | A52 Ash Bank Road | Bridle Path | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700716 | Somerton Road | Werrington | Meigh Road | Penmere Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701387 | Laurel crescent | Werrington | Somerton Road | limit of adoption app 40m north | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701094 | Beaufort Avenue | Werrington | Somerton Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700639 | Penmere Drive | Werrington | Somerton Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700849 | Wynstay Avenue | Werrington | Penmere Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701895 | Langton Close | Werrington | Meigh Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701896 | Ferndale Close | Werrington | Meigh Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701897 | Weston Close | Werrington | Meigh Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700790 | Tregaron Court | Werrington | Meigh Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700287 | Chetwynd Avenue | Werrington | Meigh Road | Holly Drive | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701199 | Holly Drive | Werrington | Chetwynd Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37701123 | Alford Drive | Werrington | Chetwynd Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1309 | 37700213 | Bridle Path | Werrington | A52 Ash Bank Road | limit of adoption app 150m north | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1339 | 37701999 | Cavendsh Road | Upper Tean | Tenford Lane | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1339 | 37702000 | Redhill Drive | Upper Tean | Cavendish Road | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1339 | 37702110 | Havensfield Drive | Upper Tean | Cavendish Road | ends | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1339 | 37701367 | Wentlows Road | Upper Tean | A522 Cheadle Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1339 | 37701504 | Wentlows Avenue | Upper Tean | Wentlows Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37700725 | Squirrel Hayes Avenue | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702012 | St Davids Way | Knypersley/Biddulph | Park Lane | approx 10m north Squirrel Hayes Avenue | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702013 | Holywell Close | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702014 | Merthyr Grove | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702015 | Coracle Grove | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702017 | Peny-y-Bont Walk | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702018 | Ruthin Grove | Knypersley/Biddulph | Peny-y-Bont Walk | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702019 | Barmouth Close | Knypersley/Biddulph | Peny-y-Bont Walk | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702016 | Ruabon Close | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702020 | Dylan Road | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1416 | 37702021 | Mostyn Close | Knypersley/Biddulph | St Davids Way | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D1425 | 37701998 | Hollinscroft Court | Lower Tean | A522 Uttoxeter Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2212 | 37701523 | Crossfield Avenue | Blythe Bridge | Stallington Road | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2212 | 37701520 | Ivy Close | Blythe Bridge | Crossfield Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2212 | 37701530 | Jasmine Close | Blythe Bridge | Crossfield Avenue | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed
D2596 | 37701669 | Nightingale Close | Lower Tean | Leigh Lane | end | Carriageway Preventative Pre-patching Works | Between March 2025 and March 2026 | Programmed