## Programme
Programme Name: |  |  |  |  | Structural Maintenance Schemes
Programme Reporting Period: |  |  |  |  | April 2025 - March 2026
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Area | Div | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
[6 empty] | Start Point | Finish Point
A0034 | N | W1(N) | 37602359 | Radford Bank | Stafford | Queensville island | Meadow Ridge | Kerbing along with footway and carriageway resurfacing | Between 2nd January 2025 and 6th May 2025 | Completed | 1
A0034 | N | W1(N) | 37602126 | Queensville Roundabout | Stafford | Island at the junction of Queensville / Silkmore Lane / Ampleforth Drive & access to Quensville retail park | Island at the junction of Queensville / Silkmore Lane / Ampleforth Drive & access to Quensville retail park | Carriageway resurfacing | Between 6th January 2025 and 15th May 2025 | Completed | 2
B5027 | N | E1(N) | 12901111 | Stone Road | Uttoxeter | Approx. 70m south Smithfield Road | Approx. 50m west Stone Road and 60m east Stone Road | Carriageway resurfacing | Between 27th May 2025 and 30th May 2025 | Completed | 3
A5187 | N | W1(N) | 37600463 | Station Road (inc Roundabout at Railway Street) | Stafford | Railway Street RAB | Train station entrance | Carriageway resurfacing | Between 14th April 2025 to 2nd May 2025 | Completed | 4
U2033 | N | N1 | 27000075 | Chester Road (Footway) | Talke | Wedgwood Road | Lichfield Road | Footway resurfacing | Between 12th May 2025 to 6th June 2025 | Completed | 5
B5368 | N | N1 | 27000454 | Lower Milehouse Ln (Jct of Morrisons supermarket) | Cross Heath | Junction of Morrisons Island | Junction area and approaches | Carriageway resurfacing | Between 9th June 2025 and 11th July 2025 | Completed | 6
A0034 | N | W1(N) | 37600336 | Lichfield Road (Surfacing Only) | Stafford | Riverway | Queensville Avenue | Minor kerbing along with carriageway resurfacing. | Between 30th June 2025 and 7th November 2025 | Ongoing | 7
A0034 | N | W1(N) | 37600336 | Lichfield Road (Drainage Only) | Stafford | Queensville Avenue | Queensville Rail Bridge | Drainage works | Between 30th June 2025 and 7th November 2025 | Ongoing | 8
B5369 | N | N1 | 27000663 | Dimsdale Parade West (Jnc B5370 Watlands View) | Dimsdale | Junction area and approaches | Junction area and approaches | Carriageway resurfacing | Between 6th October 2025 to 31st October 2025 | Programmed | 9
A0525 | N | N1 | 27001327 | Keele Road | Keele | Approx. 50m eastbound approach to ped crossing by Keele University Barnes Hall Road access | Barnes Hall Road access | Carriageway resurfacing | Between 30th June 2025 to 11th July 2025 | Completed | 10
A0520 | N | N2 | 37702170 | Cheadle Road / Main Road | Wetley Rocks | A522 Cheadle Road | A520 50mph exiting Wetley Rocks south | Carriageway resurfacing | Between 30th June 2025 to 7th November 2025 | Ongoing | 11
A0520 | N | W1(N) |  | Leek Road (Cellarhead Junction) | Cellarhead | Junction and approaches to Paton Drive | Junction and approaches to Paton Drive | Carriageway resurfacing | Between 2nd February 2026 to 28th November 2026 | Programmed | 13
A0513 | S | E3 | 39400141, 39400477 | Upper Gungate / Aldergate | Tamworth | Comberford Road | Lichfield Street | Carriageway resurfacing | Between 10th February 2025 and 4th April 2025 | Completed | 0
C0006 | S | W3 | 36700171 | Wolverhampton Road | Codsall | Church Entrance | Pedrell Close | Carriageway resurfacing | Between 7th April 2025 to 27th April 2025 | Completed | 1
A4091 | S | E3 | 23401051 | Coleshill Street - Phase 1 (Inclusive of B5404 Island & approaches) | Fazeley | Atherstone Road Island | Atherstone Road Island | Carriageway resurfacing | Between 28th April 2025 to 3rd July 2025 | Completed | 2
A4091 | S | E3 | 23401051 | Coleshill Street - Phase 2 (Inclusive of B5404 Island & approaches) | Fazeley | Watling Street | Brook End | Carriageway resurfacing | Between 15th September 2025 to 10th October 2025 | Programmed
A0515 | S | E2 | 23400268 | Lichfield Road | Wood End, Lichfield | Near Wood End Lane | Railway over bridge | Carriageway resurfacing | Between 2nd June 2025 and 13th June 2025 | Completed | 3
A5121 | S | E1(S) | 12900522 | Derby Road Phase 2 (Derby Turns Roundabout & Horninglow Road North hotspot) | Burton upon Trent | Derby Turns Roundabout and approaches | Horninglow Road North (Up to near Goodmasn Street) | Carriageway resurfacing | Between 11th August 2025 to 19th September 2025 | Ongoing | 4
A0444 | S | E1 | 12900334 | Stanton Road | Burton upon Trent | Island that serves Violet Way | Island that serves Violet Way | Carriageway resurfacing | Between 11th August 2025 to 18th August 2025 | Completed | 5
B5018 | S | E1(S) | 12900319 | Union Street Crossroad | Burton upon Trent | Crossroad that serves New Street, Orchard Street, New Street/Moor Street | Crossroad that serves New Street, Orchard Street, New Street/Moor Street | Carriageway resurfacing | Between 14th July 2025 to 5th August 2025 | Completed | 6
U4001 | S | E1 | 12900380 | Lichfield Street / New Street | Burton upon Trent | Mini roundabout junction | High Street / Manor Croft | Carriageway resurfacing | Between 14th July 2025 to 8th August 2025 | Completed | 7
B4154 | S | W2 | 5500411 | Walsall Road | Norton Canes | Norton Green Lane | Betty's Lane | Carriageway resurfacing | Between 6th April 2025 to 8th May 2025 | Programmed | 8
A0515 | S | E2 | 23400324 | Lichfield Road | Kings Bromley | From property Cherry Lodge | to the junction of Alrewas Road | Carriageway resurfacing | Between 20th October 2025 to 31st October 2025 | Programmed | 9
D3298 | S | E2 | 23400405 | Spinney Lane | Burntwood | Wordsworth Road | Birch Terrace | Carriageway reconstruction | Between 23rd June 2025 to 12th September 2025 | Ongoing | 10